## Time Line
S No | Module | Includes | Duration (days) | Start Date | End Date | Notes
1 | Auth & User Management | Phase 1 (Auth, Sessions, Token rotation) | 7 | 2025-11-14 | 2025-11-20
2 | Feed & Profiles (MVP) | Phase 2 (Posts, Profiles, Comments, Likes) | 14 | 2025-11-14 | 2025-11-27
3 | Notifications & Background Jobs | Phase 5 (Push, in‑app, FCM) | 5 | 2025-11-14 | 2025-11-18
4 | Media Uploads (MVP) | Phase 6 (Presigned URL, Upload Manager) | 4 | 2025-11-14 | 2025-11-17
5 | Observability, CI, Security baseline | Phase 7 (Crashlytics, Logs) | 4 | 2025-11-14 | 2025-11-17
6 | Android UI (MVP) | Core screens: Auth, Feed, Post, Profile | 30 | 2025-11-14 | 2025-12-13
S No | Stage of Work | Description | Status | Next Action | Link
1 | Project Ideas | Documented in TXT | Completed | No action needed
2 | Technology Finalizing | Tech stack decision (Android(kotlin), Go backend(Rest API and GraphQL), R2, MSSQL, Redis optional) | Completed | No action needed
3 | UI/UX Design | Google Stitch Project: (Provided link) | Completed | Export assets for Android & backend | https://stitch.withgoogle.com/projects/7554233729227907000?pli=1
4 | Server and Storage | Linux Server + Domain (host.co.in), Cloudflare R2 storage | Completed / Ready | Configure SSL, deploy test API
5 | Pipeline CI/CD | Auto deploy backend + Android build automation | Pending | Set up GitHub Actions (Backend + Android)
6 | Development Works (Phase 1–3) | Auth, Feed, Profile, Uploads, Notifications MVP | Started / Ongoing | Follow 30-day plan (Days 1–18)
7 | Development Works (Phase 4–7) | Advanced features (Chat, Search, Tournaments, Admin, Observability) | Planned for Post-MVP | Start after Play Store release
Day | Date | Task | Status
1 | 2025-11-14 | Project setup (backend+android), DB setup
2 | 2025-11-15 | User model, migrations, login/register APIs
3 | 2025-11-16 | OTP, TokenStore, Network, login UI
4 | 2025-11-17 | Auth integration & refresh tokens
5 | 2025-11-18 | Forgot password backend+UI
6 | 2025-11-19 | Backend deploy, migrations, SSL/CORS
7 | 2025-11-20 | Full auth testing
8 | 2025-11-21 | Post model, create/list post API
9 | 2025-11-22 | Upload handler, metadata
10 | 2025-11-23 | Feed UI + repo wiring
11 | 2025-11-24 | Create Post UI + upload
12 | 2025-11-25 | Post detail + comments
13 | 2025-11-26 | Likes API + UI
14 | 2025-11-27 | Full feed testing
15 | 2025-11-28 | Profile API + avatar
16 | 2025-11-29 | Edit profile
17 | 2025-11-30 | Notifications API, FCM token register
18 | 2025-12-01 | Android NotificationCenter
19 | 2025-12-02 | Settings, logout
20 | 2025-12-03 | Crashlytics, logs
21 | 2025-12-04 | Regression testing
22 | 2025-12-05 | Device tests, crash fixes
23 | 2025-12-06 | Play Store listing content
24 | 2025-12-07 | Build signed release
25 | 2025-12-08 | Fix Play Console issues
26 | 2025-12-09 | Final polish
27 | 2025-12-10 | Closed testing + bug fixes
28 | 2025-12-11 | Production release
29 | 2025-12-12 | Buffer/fixes
30 | 2025-12-13 | Final cleanup & Phase‑2 plan

## Project Plan List
S No | Phase | Front End File | File Path | Design File | Status
1 | Phase 1 | SplashScreen.kt | mobile/android/app/src/main/java/com/gatherup/ui/screens/onboarding/SplashScreen.kt | splash_design.fig / splash.png
2 | Phase 1 | LoginScreen.kt | mobile/android/app/src/main/java/com/gatherup/ui/screens/auth/LoginScreen.kt | login_screen.fig / login.png
3 | Phase 1 | LoginFormScreen.kt | mobile/android/app/src/main/java/com/gatherup/ui/screens/auth/LoginFormScreen.kt | login_form.fig
4 | Phase 1 | RegisterScreen.kt | mobile/android/app/src/main/java/com/gatherup/ui/screens/auth/RegisterScreen.kt | register_screen.fig
5 | Phase 1 | ForgotPasswordScreen.kt | mobile/android/app/src/main/java/com/gatherup/ui/screens/auth/ForgotPasswordScreen.kt | forgot_password.fig
6 | Phase 1 | OtpVerifyScreen.kt | mobile/android/app/src/main/java/com/gatherup/ui/screens/auth/OtpVerifyScreen.kt | otp_verify.fig
7 | Phase 1 | ResetPasswordScreen.kt | mobile/android/app/src/main/java/com/gatherup/ui/screens/auth/ResetPasswordScreen.kt | reset_password.fig
8 | Phase 1 | AuthSuccessScreen.kt | mobile/android/app/src/main/java/com/gatherup/ui/screens/auth/AuthSuccessScreen.kt | auth_success.fig
9 | Phase 1 | AuthViewModel.kt | mobile/android/app/src/main/java/com/gatherup/vm/AuthViewModel.kt | —
10 | Phase 1 | TokenStore.kt | mobile/android/app/src/main/java/com/gatherup/security/TokenStore.kt | —
11 | Phase 1 | AuthService.kt | mobile/android/app/src/main/java/com/gatherup/data/api/AuthService.kt | —
12 | Phase 1 | NetworkModule.kt | mobile/android/app/src/main/java/com/gatherup/di/NetworkModule.kt | —
13 | Phase 1 | AuthRepositoryImpl.kt | mobile/android/app/src/main/java/com/gatherup/data/repository/AuthRepositoryImpl.kt | —
14 | Phase 1 | design-tokens.json | mobile/android/app/src/main/java/com/gatherup/ui/theme/designtokens/design-tokens.json | design_tokens.fig
15 | Phase 1 | strings.xml | mobile/android/app/src/main/res/values/strings.xml | —
16 | Phase 1 | strings-ta.xml | mobile/android/app/src/main/res/values-ta/strings.xml | —
17 | Phase 2 | FeedScreen.kt | mobile/android/app/src/main/java/com/gatherup/ui/screens/FeedScreen.kt | feed_screen.fig / feed.png
18 | Phase 2 | PostDetailScreen.kt | mobile/android/app/src/main/java/com/gatherup/ui/screens/PostDetailScreen.kt | post_detail.fig
19 | Phase 2 | PostComposerScreen.kt | mobile/android/app/src/main/java/com/gatherup/ui/screens/PostComposerScreen.kt | post_composer.fig
20 | Phase 2 | PostCard.kt | mobile/android/app/src/main/java/com/gatherup/ui/components/posts/PostCard.kt | post_card.fig
21 | Phase 2 | PostActions.kt | mobile/android/app/src/main/java/com/gatherup/ui/components/posts/PostActions.kt | post_actions.fig
22 | Phase 2 | CommentItem.kt | mobile/android/app/src/main/java/com/gatherup/ui/components/posts/CommentItem.kt | comment_item.fig
23 | Phase 2 | MediaGallery.kt | mobile/android/app/src/main/java/com/gatherup/ui/components/posts/MediaGallery.kt | media_gallery.fig
24 | Phase 2 | FeedViewModel.kt | mobile/android/app/src/main/java/com/gatherup/vm/FeedViewModel.kt | —
25 | Phase 2 | PostService.kt | mobile/android/app/src/main/java/com/gatherup/data/api/PostService.kt | —
26 | Phase 2 | PostRepositoryImpl.kt | mobile/android/app/src/main/java/com/gatherup/data/repository/PostRepositoryImpl.kt | —
27 | Phase 2 | PostRemoteMediator.kt | mobile/android/app/src/main/java/com/gatherup/data/paging/PostRemoteMediator.kt | —
28 | Phase 2 | PostDao.kt | mobile/android/app/src/main/java/com/gatherup/data/local/dao/PostDao.kt | —
29 | Phase 2 | post_hashtags.fig | mobile/android/app/src/main/assets/design/post_hashtags.fig | post_hashtags.fig
30 | Phase 3 | ChatListScreen.kt | mobile/android/app/src/main/java/com/gatherup/ui/screens/ChatListScreen.kt | chat_list.fig
31 | Phase 3 | ChatThreadScreen.kt | mobile/android/app/src/main/java/com/gatherup/ui/screens/ChatThreadScreen.kt | chat_thread.fig
32 | Phase 3 | MessageBubble.kt | mobile/android/app/src/main/java/com/gatherup/ui/components/chat/MessageBubble.kt | message_bubble.fig
33 | Phase 3 | MessageComposer.kt | mobile/android/app/src/main/java/com/gatherup/ui/components/chat/MessageComposer.kt | message_composer.fig
34 | Phase 3 | ChatViewModel.kt | mobile/android/app/src/main/java/com/gatherup/vm/ChatViewModel.kt | —
35 | Phase 3 | WsClient.kt | mobile/android/app/src/main/java/com/gatherup/ws/WsClient.kt | ws_client.fig
36 | Phase 3 | WsMessageHandler.kt | mobile/android/app/src/main/java/com/gatherup/ws/WsMessageHandler.kt | ws_message_handler.fig
37 | Phase 3 | WsReconnectionManager.kt | mobile/android/app/src/main/java/com/gatherup/ws/WsReconnectionManager.kt | ws_reconnect.fig
38 | Phase 3 | MessageService.kt | mobile/android/app/src/main/java/com/gatherup/data/api/ChatService.kt | —
39 | Phase 3 | MessageRepositoryImpl.kt | mobile/android/app/src/main/java/com/gatherup/data/repository/ChatRepositoryImpl.kt | —
40 | Phase 3 | MessageRemoteMediator.kt | mobile/android/app/src/main/java/com/gatherup/data/paging/MessageRemoteMediator.kt | —
41 | Phase 3 | MessageDao.kt | mobile/android/app/src/main/java/com/gatherup/data/local/dao/MessageDao.kt | —
42 | Phase 4 | TournamentListScreen.kt | mobile/android/app/src/main/java/com/gatherup/ui/screens/TournamentListScreen.kt | tournament_list.fig
43 | Phase 4 | TournamentDetailScreen.kt | mobile/android/app/src/main/java/com/gatherup/ui/screens/TournamentDetailScreen.kt | tournament_detail.fig
44 | Phase 4 | CreateTournamentScreen.kt | mobile/android/app/src/main/java/com/gatherup/ui/screens/CreateTournamentScreen.kt | create_tournament.fig
45 | Phase 4 | LeaderboardItem.kt | mobile/android/app/src/main/java/com/gatherup/ui/components/tournaments/LeaderboardItem.kt | leaderboard_item.fig
46 | Phase 4 | MatchCard.kt | mobile/android/app/src/main/java/com/gatherup/ui/components/tournaments/MatchCard.kt | match_card.fig
47 | Phase 4 | TournamentViewModel.kt | mobile/android/app/src/main/java/com/gatherup/vm/TournamentViewModel.kt | —
48 | Phase 4 | TournamentService.kt | mobile/android/app/src/main/java/com/gatherup/data/api/TournamentService.kt | —
49 | Phase 4 | TournamentRepositoryImpl.kt | mobile/android/app/src/main/java/com/gatherup/data/repository/TournamentRepositoryImpl.kt | —
50 | Phase 4 | LeaderboardWorker.kt | mobile/android/app/src/main/java/com/gatherup/worker/leaderboard/LeaderboardWorker.kt | —
51 | Phase 5 | NotificationCenter.kt | mobile/android/app/src/main/java/com/gatherup/ui/components/notifications/NotificationCenter.kt | notification_center.fig
52 | Phase 5 | NotificationManager.kt | mobile/android/app/src/main/java/com/gatherup/notifications/NotificationManager.kt | notification_manager.fig
53 | Phase 5 | NotificationsScreen.kt | mobile/android/app/src/main/java/com/gatherup/ui/screens/NotificationsScreen.kt | notifications_screen.fig
54 | Phase 5 | SyncWorker.kt | mobile/android/app/src/main/java/com/gatherup/work/SyncWorker.kt | sync_worker.fig
55 | Phase 5 | PushTokenService.kt | mobile/android/app/src/main/java/com/gatherup/data/api/PushTokenService.kt | —
56 | Phase 5 | NotificationRepositoryImpl.kt | mobile/android/app/src/main/java/com/gatherup/data/repository/NotificationRepositoryImpl.kt | —
57 | Phase 6 | MediaGallery.kt | mobile/android/app/src/main/java/com/gatherup/ui/components/posts/MediaGallery.kt | media_gallery.fig
58 | Phase 6 | UploadManager.kt | mobile/android/app/src/main/java/com/gatherup/data/uploads/UploadManager.kt | upload_manager.fig
59 | Phase 6 | UploadHandler.kt | mobile/android/app/src/main/java/com/gatherup/storage/upload_handler.kt | —
60 | Phase 6 | PresignService.kt | mobile/android/app/src/main/java/com/gatherup/data/api/PresignService.kt | —
61 | Phase 6 | PostRemoteMediator.kt | mobile/android/app/src/main/java/com/gatherup/data/paging/PostRemoteMediator.kt | —
62 | Phase 6 | OfflineSync.kt | mobile/android/app/src/main/java/com/gatherup/work/OfflineSync.kt | offline_sync.fig
63 | Phase 7 | CrashReporter.kt | mobile/android/app/src/main/java/com/gatherup/observability/CrashReporter.kt | crash_reporter.fig
64 | Phase 7 | Analytics.kt | mobile/android/app/src/main/java/com/gatherup/observability/Analytics.kt | analytics.fig
65 | Phase 7 | android-ci.yml | mobile/android/.github/workflows/android-ci.yml | ci_spec.fig
66 | Phase 7 | detekt.yml | mobile/android/detekt.yml | detekt_config.fig
67 | Phase 7 | UiAccessibilityTest.kt | mobile/android/app/src/androidTest/java/com/gatherup/ui/UiAccessibilityTest.kt | —
68 | Phase 7 | ComponentSnapshotTest.kt | mobile/android/app/src/sharedTest/java/com/gatherup/ui/ComponentSnapshotTest.kt | —
S No | Phase | Back End File | File Path | Design File | Status
1 | Phase 1 | api/routes.go | backend/go/api/routes.go | api_routes.fig
2 | Phase 1 | api/middleware.go | backend/go/api/middleware.go | middleware_spec.fig
3 | Phase 1 | api/handlers_auth.go | backend/go/api/handlers_auth.go | auth_handlers.fig
4 | Phase 1 | auth/jwt.go | backend/go/auth/jwt.go | auth_jwt.fig
5 | Phase 1 | auth/tokens.go | backend/go/auth/tokens.go | auth_tokens.fig
6 | Phase 1 | auth/passwd_helpers.go | backend/go/auth/passwd_helpers.go | passwd_helpers.fig
7 | Phase 1 | config/config.go | backend/go/config/config.go | config_spec.fig
8 | Phase 1 | db/conn.go | backend/go/db/conn.go | db_conn.fig
9 | Phase 1 | db/migrator.go | backend/go/db/migrator.go | migrator.fig
10 | Phase 1 | db/migrations/0001_gatherup_schema_with_softdelete.sql | backend/go/db/migrations/0001_gatherup_schema_with_softdelete.sql | 0001_schema.sql
11 | Phase 1 | db/migrations/0002_seed_lookup_data.sql | backend/go/db/migrations/0002_seed_lookup_data.sql | 0002_seed.sql
12 | Phase 1 | models/user.go | backend/go/models/user.go | models_user.fig
13 | Phase 1 | repository/user_repo.go | backend/go/repository/user_repo.go | repo_user.fig
14 | Phase 1 | service/auth_service.go | backend/go/service/auth_service.go | service_auth.fig
15 | Phase 1 | proto/api.proto | backend/go/proto/api.proto | api_proto.fig
16 | Phase 1 | scripts/migrate.sh | backend/go/scripts/migrate.sh | script_migrate.fig
17 | Phase 1 | README.md | backend/go/README.md | readme.fig
18 | Phase 2 | api/handlers_posts.go | backend/go/api/handlers_posts.go | posts_handlers.fig
19 | Phase 2 | models/post.go | backend/go/models/post.go | models_post.fig
20 | Phase 2 | repository/post_repo.go | backend/go/repository/post_repo.go | repo_post.fig
21 | Phase 2 | service/post_service.go | backend/go/service/post_service.go | service_post.fig
22 | Phase 2 | search/post_search.go | backend/go/search/post_search.go | search_post.fig
23 | Phase 2 | cache/feed_cache.go | backend/go/cache/feed_cache.go | cache_feed.fig
24 | Phase 2 | data/post_dao.go (if applicable) | backend/go/data/local/dao/post_dao.go | post_dao.fig
25 | Phase 3 | api/handlers_chat.go | backend/go/api/handlers_chat.go | chat_handlers.fig
26 | Phase 3 | models/message.go | backend/go/models/message.go | models_message.fig
27 | Phase 3 | repository/message_repo.go | backend/go/repository/message_repo.go | repo_message.fig
28 | Phase 3 | service/chat_service.go | backend/go/service/chat_service.go | service_chat.fig
29 | Phase 3 | ws/hub.go | backend/go/ws/hub.go | ws_hub.fig
30 | Phase 3 | ws/connection.go | backend/go/ws/connection.go | ws_connection.fig
31 | Phase 3 | ws/router.go | backend/go/ws/router.go | ws_router.fig
32 | Phase 3 | ws/handlers.go | backend/go/ws/handlers.go | ws_handlers.fig
33 | Phase 3 | ws/redis_pubsub.go | backend/go/ws/redis_pubsub.go | ws_redis_pubsub.fig
34 | Phase 3 | tools/load-test/websocket_test.go | backend/go/tools/load-test/websocket_test.go | loadtest_ws.fig
35 | Phase 4 | api/handlers_tournaments.go | backend/go/api/handlers_tournaments.go | tournaments_handlers.fig
36 | Phase 4 | models/tournament.go | backend/go/models/tournament.go | models_tournament.fig
37 | Phase 4 | repository/tournament_repo.go | backend/go/repository/tournament_repo.go | repo_tournament.fig
38 | Phase 4 | service/tournament_service.go | backend/go/service/tournament_service.go | service_tournament.fig
39 | Phase 4 | worker/leaderboard.go | backend/go/worker/leaderboard.go | worker_leaderboard.fig
40 | Phase 5 | api/handlers_notifications.go | backend/go/api/handlers_notifications.go | notifications_handlers.fig
41 | Phase 5 | models/notification.go | backend/go/models/notification.go | models_notification.fig
42 | Phase 5 | repository/notification_repo.go | backend/go/repository/notification_repo.go | repo_notification.fig
43 | Phase 5 | service/notification_service.go | backend/go/service/notification_service.go | service_notification.fig
44 | Phase 5 | worker/notifier.go | backend/go/worker/notifier.go | worker_notifier.fig
45 | Phase 5 | taskqueue/taskqueue.go | backend/go/taskqueue/taskqueue.go | taskqueue.fig
46 | Phase 5 | taskqueue/redis_queue.go | backend/go/taskqueue/redis_queue.go | taskqueue_redis.fig
47 | Phase 6 | storage/r2_client.go | backend/go/storage/r2_client.go | storage_r2.fig
48 | Phase 6 | storage/upload_handler.go | backend/go/storage/upload_handler.go | storage_upload.fig
49 | Phase 6 | storage/file_utils.go | backend/go/storage/file_utils.go | storage_utils.fig
50 | Phase 6 | scripts/seed_sample_data.sh (if upload samples) | backend/go/scripts/seed_sample_data.sh | script_seed.fig
51 | Phase 6 | infra/docker/Dockerfile.api (for uploads) | backend/go/infra/docker/Dockerfile.api | docker_api.fig
52 | Phase 7 | cmd/server/main.go | backend/go/cmd/server/main.go | server_main.fig
53 | Phase 7 | cmd/worker/main.go | backend/go/cmd/worker/main.go | worker_main.fig
54 | Phase 7 | shared/types.go | backend/go/shared/types.go | shared_types.fig
55 | Phase 7 | shared/constants.go | backend/go/shared/constants.go | shared_constants.fig
56 | Phase 7 | shared/utils.go | backend/go/shared/utils.go | shared_utils.fig
57 | Phase 7 | internal/errors.go | backend/go/internal/errors.go | internal_errors.fig
58 | Phase 7 | internal/validators.go | backend/go/internal/validators.go | internal_validators.fig
59 | Phase 7 | internal/serializers.go | backend/go/internal/serializers.go | internal_serializers.fig
60 | Phase 7 | pkg/logger/logger.go | backend/go/pkg/logger/logger.go | pkg_logger.fig
61 | Phase 7 | pkg/metrics/metrics.go | backend/go/pkg/metrics/metrics.go | pkg_metrics.fig
62 | Phase 7 | taskqueue/tasks.go | backend/go/taskqueue/tasks.go | taskqueue_tasks.fig
63 | Phase 7 | search/elasticsearch.go | backend/go/search/elasticsearch.go | search_es.fig
64 | Phase 7 | proto/message.proto | backend/go/proto/message.proto | message_proto.fig
65 | Phase 7 | tools/dev-compose.yml | backend/go/tools/dev-compose.yml | dev_compose.fig
66 | Phase 7 | infra/docker/docker-compose.prod.yml | backend/go/infra/docker/docker-compose.prod.yml | docker_compose_prod.fig
67 | Phase 7 | infra/k8s/api-deployment.yaml | backend/go/infra/k8s/api-deployment.yaml | k8s_api_deploy.fig
68 | Phase 7 | infra/k8s/ws-deployment.yaml | backend/go/infra/k8s/ws-deployment.yaml | k8s_ws_deploy.fig
69 | Phase 7 | infra/k8s/worker-deployment.yaml | backend/go/infra/k8s/worker-deployment.yaml | k8s_worker_deploy.fig
70 | Phase 7 | infra/k8s/service.yaml | backend/go/infra/k8s/service.yaml | k8s_service.fig
71 | Phase 7 | .github/workflows/ci.yml | backend/go/.github/workflows/ci.yml | ci_backend.fig
72 | Phase 7 | .github/workflows/security-scan.yml | backend/go/.github/workflows/security-scan.yml | security_scan.fig
73 | Phase 7 | Makefile | backend/go/Makefile | —
74 | Phase 7 | .env.example | backend/go/.env.example | —
75 | Phase 7 | go.mod | backend/go/go.mod | —
76 | Phase 7 | go.sum | backend/go/go.sum | —
77 | Phase 7 | README.md | backend/go/README.md | —

## API
S No | Phase | API Path | Method | Purpose | Auth Required | Backend Files | Frontend Files | Notes | Backend_Place_Comment | Frontend_Place_Comment | Status | Postman Test | Deploy Status
1 | Phase 1 | /auth/register | POST | Register new user | No | backend/go/api/handlers_auth.go | AuthService.kt | Returns tokens | /* Place: backend/go/api/handlers_auth.go */ | /* Place: mobile/android/app/src/main/java/com/gatherup/AuthService.kt */
2 | Phase 1 | /auth/login | POST | Login with credentials | No | backend/go/api/handlers_auth.go | AuthService.kt | Support MFA/OTP | /* Place: backend/go/api/handlers_auth.go */ | /* Place: mobile/android/app/src/main/java/com/gatherup/AuthService.kt */
3 | Phase 1 | /auth/refresh | POST | Refresh access token | No (refresh token) | backend/go/api/handlers_auth.go | NetworkModule.kt | Rotate refresh token | /* Place: backend/go/api/handlers_auth.go */ | /* Place: mobile/android/app/src/main/java/com/gatherup/NetworkModule.kt */
4 | Phase 1 | /auth/logout | POST | Revoke refresh token | Yes | backend/go/api/handlers_auth.go | AuthRepositoryImpl.kt | Revoke by session | /* Place: backend/go/api/handlers_auth.go */ | /* Place: mobile/android/app/src/main/java/com/gatherup/AuthRepositoryImpl.kt */
5 | Phase 1 | /auth/send-otp | POST | Send OTP to phone | No | backend/go/api/handlers_auth.go | Otp screens | Rate-limited | /* Place: backend/go/api/handlers_auth.go */ | /* Place: mobile/android/app/src/main/java/com/gatherup/Otp screens */
6 | Phase 1 | /auth/verify-otp | POST | Verify OTP | No | backend/go/api/handlers_auth.go | OtpVerifyScreen.kt |  | /* Place: backend/go/api/handlers_auth.go */ | /* Place: mobile/android/app/src/main/java/com/gatherup/OtpVerifyScreen.kt */
7 | Phase 1 | /auth/password-reset/request | POST | Request password reset | No | backend/go/api/handlers_auth.go |  | Email/OTP | /* Place: backend/go/api/handlers_auth.go */
8 | Phase 1 | /auth/password-reset/confirm | POST | Confirm password reset | No | backend/go/api/handlers_auth.go |  |  | /* Place: backend/go/api/handlers_auth.go */
9 | Phase 1 | /auth/password-change | POST | Change password (authenticated) | Yes | backend/go/api/handlers_auth.go | SettingsScreen.kt | NEW | /* Place: backend/go/api/handlers_auth.go */ | /* Place: mobile/android/app/src/main/java/com/gatherup/SettingsScreen.kt */
10 | Phase 1 | /auth/email-verify/request | POST | Request email verification | Yes | backend/go/api/handlers_auth.go | ProfileScreen.kt | NEW | /* Place: backend/go/api/handlers_auth.go */ | /* Place: mobile/android/app/src/main/java/com/gatherup/ProfileScreen.kt */
11 | Phase 1 | /auth/email-verify/confirm | POST | Confirm email verification | Yes | backend/go/api/handlers_auth.go | ProfileScreen.kt | NEW | /* Place: backend/go/api/handlers_auth.go */ | /* Place: mobile/android/app/src/main/java/com/gatherup/ProfileScreen.kt */
12 | Phase 1 | /auth/phone-verify/request | POST | Request phone verification | Yes | backend/go/storage/upload_handler.go | ProfileScreen.kt | NEW | /* Place: backend/go/storage/upload_handler.go */ | /* Place: mobile/android/app/src/main/java/com/gatherup/ProfileScreen.kt */
13 | Phase 1 | /auth/phone-verify/confirm | POST | Confirm phone verification | Yes | backend/go/api/handlers_auth.go | ProfileScreen.kt | NEW | /* Place: backend/go/api/handlers_auth.go */ | /* Place: mobile/android/app/src/main/java/com/gatherup/ProfileScreen.kt */
14 | Phase 1 | /auth/token-introspect | POST | Introspect token | Yes (admin) | backend/go/api/handlers_auth.go |  | Debug endpoint | /* Place: backend/go/api/handlers_auth.go */
15 | Phase 1 | /auth/sessions | GET | List user sessions | Yes | backend/go/api/handlers_auth.go | Settings UI |  | /* Place: backend/go/api/handlers_auth.go */ | /* Place: mobile/android/app/src/main/java/com/gatherup/Settings UI */
16 | Phase 1 | /auth/sessions/{session_id}/revoke | POST | Revoke specific session | Yes | backend/go/api/handlers_auth.go |  |  | /* Place: backend/go/api/handlers_auth.go */
17 | Phase 1 | /auth/sessions/revoke-all | POST | Revoke all other sessions | Yes | backend/go/api/handlers_auth.go | SettingsScreen.kt | NEW | /* Place: backend/go/api/handlers_auth.go */ | /* Place: mobile/android/app/src/main/java/com/gatherup/SettingsScreen.kt */
18 | Phase 1/2 | /users/{id} | GET | Get user public profile | No/Opt | backend/go/api/handlers_user.go | Profile screen |  | /* Place: backend/go/api/handlers_user.go */ | /* Place: mobile/android/app/src/main/java/com/gatherup/Profile screen */
19 | Phase 1 | /users/me | GET | Get current user profile | Yes | backend/go/api/handlers_user.go | Profile screen |  | /* Place: backend/go/api/handlers_user.go */ | /* Place: mobile/android/app/src/main/java/com/gatherup/Profile screen */
20 | Phase 2 | /users/me | PUT/PATCH | Update current user profile | Yes | backend/go/api/handlers_user.go | Profile edit screen |  | /* Place: backend/go/api/handlers_user.go */ | /* Place: mobile/android/app/src/main/java/com/gatherup/Profile edit screen */
21 | Phase 2 | /users/me/delete | POST | Delete account (soft) | Yes | backend/go/api/handlers_user.go | SettingsScreen.kt | NEW | /* Place: backend/go/api/handlers_user.go */ | /* Place: mobile/android/app/src/main/java/com/gatherup/SettingsScreen.kt */
22 | Phase 2 | /users/me/export | GET | Export user data | Yes | backend/go/api/handlers_user.go | SettingsScreen.kt | NEW | /* Place: backend/go/api/handlers_user.go */ | /* Place: mobile/android/app/src/main/java/com/gatherup/SettingsScreen.kt */
23 | Phase 2 | /users/{id}/avatar | POST | Upload avatar | Yes | backend/go/storage/upload_handler.go | Profile edit screen |  | /* Place: backend/go/storage/upload_handler.go */ | /* Place: mobile/android/app/src/main/java/com/gatherup/Profile edit screen */
24 | Phase 2 | /users/{id}/follow | POST | Follow a user | Yes | backend/go/api/handlers_user.go | Follow button |  | /* Place: backend/go/api/handlers_user.go */ | /* Place: mobile/android/app/src/main/java/com/gatherup/Follow button */
25 | Phase 2 | /users/{id}/unfollow | POST | Unfollow a user | Yes | backend/go/api/handlers_user.go |  |  | /* Place: backend/go/api/handlers_user.go */
26 | Phase 2 | /users/{id}/followers | GET | List followers | Opt/Yes | backend/go/repository/contacts.go | Followers list UI |  | /* Place: backend/go/repository/contacts.go */ | /* Place: mobile/android/app/src/main/java/com/gatherup/Followers list UI */
27 | Phase 2 | /users/{id}/following | GET | List following | Opt/Yes | backend/go/repository/contacts.go |  |  | /* Place: backend/go/repository/contacts.go */
28 | Phase 2 | /users/{id}/skills | GET/POST/PUT/DELETE | CRUD user skills | Yes | backend/go/repository/user_skills.go | Profile skills UI |  | /* Place: backend/go/repository/user_skills.go */ | /* Place: mobile/android/app/src/main/java/com/gatherup/Profile skills UI */
29 | Phase 2 | /users/{id}/preferences | GET/PUT | Get/update user preferences | Yes | backend/go/repository/user_preferences.go | Settings screen |  | /* Place: backend/go/repository/user_preferences.go */ | /* Place: mobile/android/app/src/main/java/com/gatherup/Settings screen */
30 | Phase 2 | /users/search/suggest | GET | User search suggestions | Opt | backend/go/search/user_search.go | Search UI | NEW | /* Place: backend/go/search/user_search.go */ | /* Place: mobile/android/app/src/main/java/com/gatherup/Search UI */
31 | Phase 2 | /contacts | GET | List contacts/friends | Yes | backend/go/api/handlers_user.go |  |  | /* Place: backend/go/api/handlers_user.go */
32 | Phase 2 | /contacts/invite | POST | Send contact invite | Yes | backend/go/api/handlers_user.go |  |  | /* Place: backend/go/api/handlers_user.go */
33 | Phase 2 | /contacts/{id}/accept | POST | Accept contact invite | Yes | backend/go/api/handlers_user.go |  |  | /* Place: backend/go/api/handlers_user.go */
34 | Phase 2 | /contacts/{id}/reject | POST | Reject invite | Yes | backend/go/api/handlers_user.go |  |  | /* Place: backend/go/api/handlers_user.go */
35 | Phase 2 | /contacts/bulk-action | POST | Bulk contact actions | Yes | backend/go/api/handlers_user.go | Contacts UI | NEW | /* Place: backend/go/api/handlers_user.go */ | /* Place: mobile/android/app/src/main/java/com/gatherup/Contacts UI */
36 | Phase 2 | /blocks | POST/DELETE | Block/unblock user | Yes | backend/go/api/handlers_user.go |  |  | /* Place: backend/go/api/handlers_user.go */
37 | Phase 2 | /posts | POST | Create a post | Yes | backend/go/api/handlers_posts.go | PostComposerScreen.kt |  | /* Place: backend/go/api/handlers_posts.go */ | /* Place: mobile/android/app/src/main/java/com/gatherup/PostComposerScreen.kt */
38 | Phase 2 | /posts | GET | List posts (paginated) | Opt | backend/go/api/handlers_posts.go | FeedScreen.kt |  | /* Place: backend/go/api/handlers_posts.go */ | /* Place: mobile/android/app/src/main/java/com/gatherup/FeedScreen.kt */
39 | Phase 2 | /posts/{id} | GET | Retrieve post by id | Opt | backend/go/api/handlers_posts.go | PostDetailScreen.kt |  | /* Place: backend/go/api/handlers_posts.go */ | /* Place: mobile/android/app/src/main/java/com/gatherup/PostDetailScreen.kt */
40 | Phase 2 | /posts/{id} | PUT/PATCH | Update post | Yes (author) | backend/go/api/handlers_posts.go |  |  | /* Place: backend/go/api/handlers_posts.go */
41 | Phase 2 | /posts/{id} | DELETE | Soft-delete post | Yes | backend/go/api/handlers_posts.go |  |  | /* Place: backend/go/api/handlers_posts.go */
42 | Phase 2 | /posts/{id}/media | POST | Attach media to post | Yes | backend/go/storage/upload_handler.go | UploadManager |  | /* Place: backend/go/storage/upload_handler.go */ | /* Place: mobile/android/app/src/main/java/com/gatherup/UploadManager */
43 | Phase 2 | /posts/{id}/views | POST | Increment view count | No/Opt | backend/go/repository/post_views.go |  | Rate-limited | /* Place: backend/go/repository/post_views.go */
44 | Phase 2 | /posts/{id}/reactions | POST/DELETE | Add/remove reaction | Yes | backend/go/repository/post_reactions.go |  |  | /* Place: backend/go/repository/post_reactions.go */
45 | Phase 2 | /posts/{id}/comments | GET/POST | List/create comments | Opt/Yes | backend/go/api/handlers_posts.go |  |  | /* Place: backend/go/api/handlers_posts.go */
46 | Phase 2 | /posts/{id}/shares | POST | Share a post | Yes | backend/go/api/handlers_posts.go |  |  | /* Place: backend/go/api/handlers_posts.go */
47 | Phase 2 | /posts/{id}/bookmark | POST/DELETE | Bookmark/unbookmark post | Yes | backend/go/api/handlers_posts.go | PostCard.kt | NEW | /* Place: backend/go/api/handlers_posts.go */ | /* Place: mobile/android/app/src/main/java/com/gatherup/PostCard.kt */
48 | Phase 2 | /posts/{id}/report | POST | Report post | Yes | backend/go/api/handlers_posts.go | PostCard.kt | NEW | /* Place: backend/go/api/handlers_posts.go */ | /* Place: mobile/android/app/src/main/java/com/gatherup/PostCard.kt */
49 | Phase 2 | /posts/search | GET | Search posts | Opt | backend/go/search/post_search.go | Search UI |  | /* Place: backend/go/search/post_search.go */ | /* Place: mobile/android/app/src/main/java/com/gatherup/Search UI */
50 | Phase 2 | /posts/bulk-delete | POST | Bulk delete posts | Yes | backend/go/api/handlers_posts.go | ProfileScreen.kt | NEW | /* Place: backend/go/api/handlers_posts.go */ | /* Place: mobile/android/app/src/main/java/com/gatherup/ProfileScreen.kt */
51 | Phase 2 | /posts/feed/personalized | GET | Personalized feed | Yes | backend/go/api/handlers_posts.go | FeedScreen.kt | NEW | /* Place: backend/go/api/handlers_posts.go */ | /* Place: mobile/android/app/src/main/java/com/gatherup/FeedScreen.kt */
52 | Phase 2 | /bookmarks | GET | List bookmarked posts | Yes | backend/go/api/handlers_posts.go | ProfileScreen.kt | NEW | /* Place: backend/go/api/handlers_posts.go */ | /* Place: mobile/android/app/src/main/java/com/gatherup/ProfileScreen.kt */
53 | Phase 2 | /comments/{comment_id} | GET | Get comment | Opt | backend/go/repository/comments.go |  |  | /* Place: backend/go/repository/comments.go */
54 | Phase 2 | /comments/{comment_id} | PUT/PATCH | Edit comment | Yes | backend/go/api/handlers_posts.go |  |  | /* Place: backend/go/api/handlers_posts.go */
55 | Phase 2 | /comments/{comment_id} | DELETE | Delete comment | Yes | backend/go/api/handlers_posts.go |  |  | /* Place: backend/go/api/handlers_posts.go */
56 | Phase 2 | /comments/{comment_id}/reactions | POST/DELETE | React to comment | Yes | backend/go/repository/comment_reactions.go |  |  | /* Place: backend/go/repository/comment_reactions.go */
57 | Phase 2 | /comments/{comment_id}/report | POST | Report comment | Yes | backend/go/api/handlers_posts.go | CommentItem.kt | NEW | /* Place: backend/go/api/handlers_posts.go */ | /* Place: mobile/android/app/src/main/java/com/gatherup/CommentItem.kt */
58 | Phase 6 | /uploads/presign | POST | Create presigned PUT URL | Yes | backend/go/storage/r2_client.go | UploadManager.kt |  | /* Place: backend/go/storage/r2_client.go */ | /* Place: mobile/android/app/src/main/java/com/gatherup/UploadManager.kt */
59 | Phase 6 | /uploads/complete | POST | Confirm upload | Yes | backend/go/storage/upload_handler.go |  |  | /* Place: backend/go/storage/upload_handler.go */
60 | Phase 6 | /uploads/{media_id} | GET | Serve media via CDN | No | backend/go/storage/r2_client.go | Media viewer |  | /* Place: backend/go/storage/r2_client.go */ | /* Place: mobile/android/app/src/main/java/com/gatherup/Media viewer */
61 | Phase 6 | /uploads/{media_id}/thumb | GET | Serve thumbnail | No | backend/go/storage/file_utils.go |  |  | /* Place: backend/go/storage/file_utils.go */
62 | Phase 6 | /storage/validate | POST | Validate file metadata | Yes | backend/go/storage/file_utils.go |  |  | /* Place: backend/go/storage/file_utils.go */
63 | Phase 6 | /media/cleanup | POST | Trigger cleanup | Yes (admin) | worker/cleanup.go |  |  | /* Place: worker/cleanup.go */
64 | Phase 3 | /ws | WS (upgrade) | WebSocket endpoint | Yes | backend/go/ws/router.go | WsClient.kt |  | /* Place: backend/go/ws/router.go */ | /* Place: mobile/android/app/src/main/java/com/gatherup/WsClient.kt */
65 | Phase 3 | /chats | POST | Create chat | Yes | backend/go/api/handlers_chat.go | Create group chat screen |  | /* Place: backend/go/api/handlers_chat.go */ | /* Place: mobile/android/app/src/main/java/com/gatherup/Create group chat screen */
66 | Phase 3 | /chats | GET | List user's chats | Yes | backend/go/api/handlers_chat.go | Chat list screen |  | /* Place: backend/go/api/handlers_chat.go */ | /* Place: mobile/android/app/src/main/java/com/gatherup/Chat list screen */
67 | Phase 3 | /chats/{id} | GET | Get chat metadata | Yes | backend/go/repository/chats.go |  |  | /* Place: backend/go/repository/chats.go */
68 | Phase 3 | /chats/{id}/participants | POST/DELETE | Add/remove participant | Yes | backend/go/repository/chat_participants.go |  |  | /* Place: backend/go/repository/chat_participants.go */
69 | Phase 3 | /chats/{id}/history | GET | Get messages (paged) | Yes | backend/go/api/handlers_chat.go | ChatThreadScreen.kt |  | /* Place: backend/go/api/handlers_chat.go */ | /* Place: mobile/android/app/src/main/java/com/gatherup/ChatThreadScreen.kt */
70 | Phase 3 | /chats/{id}/typing | POST | Send typing indicator | Yes | backend/go/api/handlers_chat.go | MessageComposer.kt | NEW | /* Place: backend/go/api/handlers_chat.go */ | /* Place: mobile/android/app/src/main/java/com/gatherup/MessageComposer.kt */
71 | Phase 3 | /chats/{id}/mark-read | POST | Mark chat as read | Yes | backend/go/api/handlers_chat.go | ChatThreadScreen.kt | NEW | /* Place: backend/go/api/handlers_chat.go */ | /* Place: mobile/android/app/src/main/java/com/gatherup/ChatThreadScreen.kt */
72 | Phase 3 | /messages/{id} | GET | Get message by id | Yes | backend/go/repository/message_repo.go |  |  | /* Place: backend/go/repository/message_repo.go */
73 | Phase 3 | /messages/{id} | DELETE | Delete message | Yes | backend/go/api/handlers_chat.go |  |  | /* Place: backend/go/api/handlers_chat.go */
74 | Phase 3 | /messages/{id}/edit | PATCH | Edit message | Yes | backend/go/api/handlers_chat.go | MessageBubble.kt | NEW | /* Place: backend/go/api/handlers_chat.go */ | /* Place: mobile/android/app/src/main/java/com/gatherup/MessageBubble.kt */
75 | Phase 3 | /messages/{id}/react | POST | React to message | Yes | backend/go/api/handlers_chat.go | MessageBubble.kt | NEW | /* Place: backend/go/api/handlers_chat.go */ | /* Place: mobile/android/app/src/main/java/com/gatherup/MessageBubble.kt */
76 | Phase 3 | /chats/{id}/mute | POST | Mute/unmute chat | Yes | backend/go/repository/muted_chats.go |  |  | /* Place: backend/go/repository/muted_chats.go */
77 | Phase 3 | /chats/{id}/read-cursor | POST | Set last read cursor | Yes | backend/go/repository/chat_read_cursors.go |  |  | /* Place: backend/go/repository/chat_read_cursors.go */
78 | Phase 3 | WS:event:message.send | WS | Send message | Yes | backend/go/ws/handlers.go | WsClient.kt |  | /* Place: backend/go/ws/handlers.go */ | /* Place: mobile/android/app/src/main/java/com/gatherup/WsClient.kt */
79 | Phase 3 | WS:event:message.deliver | WS | Deliver message | Yes | backend/go/ws/hub.go | WsClient.kt |  | /* Place: backend/go/ws/hub.go */ | /* Place: mobile/android/app/src/main/java/com/gatherup/WsClient.kt */
80 | Phase 3 | WS:event:typing.start/stop | WS | Typing indicators | Yes | backend/go/ws/handlers.go | Typing indicator |  | /* Place: backend/go/ws/handlers.go */ | /* Place: mobile/android/app/src/main/java/com/gatherup/Typing indicator */
81 | Phase 3 | WS:event:presence.update | WS | Presence updates | Yes | backend/go/ws/handlers.go | Online status | NEW | /* Place: backend/go/ws/handlers.go */ | /* Place: mobile/android/app/src/main/java/com/gatherup/Online status */
82 | Phase 4 | /tournaments | POST | Create tournament | Yes | backend/go/api/handlers_tournaments.go | CreateTournamentScreen.kt |  | /* Place: backend/go/api/handlers_tournaments.go */ | /* Place: mobile/android/app/src/main/java/com/gatherup/CreateTournamentScreen.kt */
83 | Phase 4 | /tournaments | GET | List tournaments | Opt | backend/go/api/handlers_tournaments.go | TournamentListScreen.kt |  | /* Place: backend/go/api/handlers_tournaments.go */ | /* Place: mobile/android/app/src/main/java/com/gatherup/TournamentListScreen.kt */
84 | Phase 4 | /tournaments/{id} | GET | Get tournament detail | Opt | backend/go/repository/tournament_repo.go | TournamentDetailScreen.kt |  | /* Place: backend/go/repository/tournament_repo.go */ | /* Place: mobile/android/app/src/main/java/com/gatherup/TournamentDetailScreen.kt */
85 | Phase 4 | /tournaments/{id} | PUT/PATCH | Update tournament | Yes | backend/go/api/handlers_tournaments.go |  |  | /* Place: backend/go/api/handlers_tournaments.go */
86 | Phase 4 | /tournaments/{id}/join | POST | Join tournament | Yes | backend/go/repository/tournament_participants.go | TournamentDetailScreen.kt |  | /* Place: backend/go/repository/tournament_participants.go */ | /* Place: mobile/android/app/src/main/java/com/gatherup/TournamentDetailScreen.kt */
87 | Phase 4 | /tournaments/{id}/leave | POST | Leave tournament | Yes | backend/go/api/handlers_tournaments.go |  |  | /* Place: backend/go/api/handlers_tournaments.go */
88 | Phase 4 | /tournaments/{id}/matches | GET | List matches | Opt | backend/go/repository/tournament_matches.go |  |  | /* Place: backend/go/repository/tournament_matches.go */
89 | Phase 4 | /tournaments/{id}/matches/{match_id}/result | POST | Submit match result | Yes | backend/go/service/tournament_service.go |  |  | /* Place: backend/go/service/tournament_service.go */
90 | Phase 4 | /tournaments/{id}/leaderboard | GET | Get leaderboard | Opt | backend/go/repository/tournament_leaderboard.go | Leaderboard UI |  | /* Place: backend/go/repository/tournament_leaderboard.go */ | /* Place: mobile/android/app/src/main/java/com/gatherup/Leaderboard UI */
91 | Phase 4 | /tournaments/{id}/share | POST | Share tournament | Yes | backend/go/repository/tournament_shares.go |  |  | /* Place: backend/go/repository/tournament_shares.go */
92 | Phase 4 | /tournaments/{id}/participants | GET | List participants | Opt | backend/go/api/handlers_tournaments.go | TournamentDetailScreen.kt | NEW | /* Place: backend/go/api/handlers_tournaments.go */ | /* Place: mobile/android/app/src/main/java/com/gatherup/TournamentDetailScreen.kt */
93 | Phase 4 | /tournaments/{id}/report | POST | Report tournament | Yes | backend/go/api/handlers_tournaments.go | TournamentDetailScreen.kt | NEW | /* Place: backend/go/api/handlers_tournaments.go */ | /* Place: mobile/android/app/src/main/java/com/gatherup/TournamentDetailScreen.kt */
94 | Phase 4/Worker | /jobs | GET | List jobs/status | Yes (admin) | backend/go/worker/jobs.go |  |  | /* Place: backend/go/worker/jobs.go */
95 | Phase 4/Worker | /jobs/{id}/retry | POST | Retry job | Yes (admin) | backend/go/worker/jobs.go |  |  | /* Place: backend/go/worker/jobs.go */
96 | Phase 4/Worker | /leaderboards/{tournament_id} | GET | Get computed leaderboard | Opt | backend/go/worker/leaderboard.go |  |  | /* Place: backend/go/worker/leaderboard.go */
97 | Phase 5 | /notifications | GET | List notifications | Yes | backend/go/api/handlers_notifications.go | NotificationCenter.kt |  | /* Place: backend/go/api/handlers_notifications.go */ | /* Place: mobile/android/app/src/main/java/com/gatherup/NotificationCenter.kt */
98 | Phase 5 | /notifications/{id}/mark-read | POST | Mark notification read | Yes | backend/go/api/handlers_notifications.go |  |  | /* Place: backend/go/api/handlers_notifications.go */
99 | Phase 5 | /notifications/mark-all-read | POST | Mark all as read | Yes | backend/go/api/handlers_notifications.go | NotificationCenter.kt | NEW | /* Place: backend/go/api/handlers_notifications.go */ | /* Place: mobile/android/app/src/main/java/com/gatherup/NotificationCenter.kt */
100 | Phase 5 | /notifications/bulk-action | POST | Bulk notification actions | Yes | backend/go/api/handlers_notifications.go | NotificationCenter.kt | NEW | /* Place: backend/go/api/handlers_notifications.go */ | /* Place: mobile/android/app/src/main/java/com/gatherup/NotificationCenter.kt */
101 | Phase 5 | /notifications/settings | GET/PUT | Notification settings | Yes | backend/go/api/handlers_notifications.go | SettingsScreen.kt | NEW | /* Place: backend/go/api/handlers_notifications.go */ | /* Place: mobile/android/app/src/main/java/com/gatherup/SettingsScreen.kt */
102 | Phase 5 | /notifications/subscribe | POST | Register push token | Yes | backend/go/repository/user_devices.go | NotificationManager.kt |  | /* Place: backend/go/repository/user_devices.go */ | /* Place: mobile/android/app/src/main/java/com/gatherup/NotificationManager.kt */
103 | Phase 5 | /notifications/unsubscribe | POST | Remove push token | Yes | backend/go/repository/user_devices.go |  |  | /* Place: backend/go/repository/user_devices.go */
104 | Phase 5 | /notifications/send | POST | Send push notification | Internal/admin | backend/go/worker/notifier.go |  |  | /* Place: backend/go/worker/notifier.go */
105 | Phase 2/7 | /search/posts | GET | Search posts | Opt | backend/go/search/elasticsearch.go | Search UI |  | /* Place: backend/go/search/elasticsearch.go */ | /* Place: mobile/android/app/src/main/java/com/gatherup/Search UI */
106 | Phase 2/7 | /search/users | GET | Search users | Opt | backend/go/search/user_search.go |  |  | /* Place: backend/go/search/user_search.go */
107 | Phase 2/7 | /search/tournaments | GET | Search tournaments | Opt | backend/go/search/tournament_search.go |  |  | /* Place: backend/go/search/tournament_search.go */
108 | Phase 2/7 | /search/global | GET | Global search | Opt | backend/go/search/global_search.go | Search UI | NEW | /* Place: backend/go/search/global_search.go */ | /* Place: mobile/android/app/src/main/java/com/gatherup/Search UI */
109 | Phase 7 | /health | GET | Health check | No | backend/go/api/handlers_health.go |  |  | /* Place: backend/go/api/handlers_health.go */
110 | Phase 7 | /health/detailed | GET | Detailed health check | Internal | backend/go/api/handlers_health.go |  | NEW | /* Place: backend/go/api/handlers_health.go */
111 | Phase 7 | /metrics | GET | Prometheus metrics | No/Internal | backend/go/pkg/metrics/metrics.go |  |  | /* Place: backend/go/pkg/metrics/metrics.go */
112 | Phase 7 | /telemetry/logs | POST | Push logs | Internal/Auth | backend/go/pkg/logger/logger.go |  |  | /* Place: backend/go/pkg/logger/logger.go */
113 | Phase 7 | /audit/logs | GET | Query audit logs | Yes (admin) | backend/go/repository/audit_logs.go |  |  | /* Place: backend/go/repository/audit_logs.go */
114 | Phase 7 | /admin/users | GET/PUT/DELETE | Manage users | Yes (admin) | backend/go/api/handlers_admin.go |  |  | /* Place: backend/go/api/handlers_admin.go */
115 | Phase 7 | /admin/posts | GET/DELETE/PATCH | Moderate posts | Yes (admin) | backend/go/api/handlers_admin.go |  |  | /* Place: backend/go/api/handlers_admin.go */
116 | Phase 7 | /admin/metrics | GET | System metrics | Yes (admin) | backend/go/api/handlers_admin.go |  |  | /* Place: backend/go/api/handlers_admin.go */
117 | Phase 7 | /admin/migrations/run | POST | Trigger DB migration | Yes (admin) | backend/go/db/migrator.go |  |  | /* Place: backend/go/db/migrator.go */
118 | Phase 7 | /admin/cache/purge | POST | Purge cache | Yes (admin) | backend/go/cache/redis.go |  |  | /* Place: backend/go/cache/redis.go */
119 | Phase 7 | /admin/reports | GET | List content reports | Yes (admin) | backend/go/api/handlers_admin.go |  | NEW | /* Place: backend/go/api/handlers_admin.go */
120 | Phase 7 | /admin/reports/{id}/resolve | POST | Resolve report | Yes (admin) | backend/go/api/handlers_admin.go |  | NEW | /* Place: backend/go/api/handlers_admin.go */
121 | Phase 7 | /admin/analytics/usage | GET | Usage analytics | Yes (admin) | backend/go/api/handlers_admin.go |  | NEW | /* Place: backend/go/api/handlers_admin.go */
122 | Phase 7 | /admin/system/config | GET/PUT | System configuration | Yes (admin) | backend/go/api/handlers_admin.go |  | NEW | /* Place: backend/go/api/handlers_admin.go */
123 | Worker | task:notifications.send | TASK | Send notifications | Internal | taskqueue/taskqueue.go |  |  | /* Place: taskqueue/taskqueue.go */
124 | Worker | task:leaderboard.compute | TASK | Compute leaderboards | Internal | worker/leaderboard.go |  |  | /* Place: worker/leaderboard.go */
125 | Worker | task:post.view_count.update | TASK | Aggregate view counts | Internal | worker/jobs.go |  |  | /* Place: worker/jobs.go */
126 | Worker | task:media.cleanup | TASK | Cleanup orphaned media | Internal | worker/cleanup.go |  |  | /* Place: worker/cleanup.go */
127 | Worker | task:feed.recommendations | TASK | Generate recommendations | Internal | worker/recommendations.go |  | NEW | /* Place: worker/recommendations.go */
128 | Worker | task:user.cleanup | TASK | Cleanup inactive users | Internal | worker/cleanup.go |  | NEW | /* Place: worker/cleanup.go */